## Project Export
Project | Project Status | Start Date | End Date | Budget | Actual Spend | Task Name | Task Status | Priority | Assignee | Sprint | Previous Sprints | Comments
Alpha | In Progress | 2026-01-06 | 2026-06-30 | 100000 | 45000 | Design system architecture | Done | High | Alice Chen | Sprint 3 |  | Completed ahead of schedule
Alpha | In Progress | 2026-01-06 | 2026-06-30 | 100000 | 45000 | Build user authentication API | In Progress | High | Bob Martinez | Sprint 5 |  | Blocked by infrastructure team - no ETA provided
Alpha | In Progress | 2026-01-06 | 2026-06-30 | 100000 | 45000 | Implement payment gateway | Blocked | Critical | Charlie Kim | Sprint 5 | Sprint 3;Sprint 4 | Blocked by third-party vendor API changes. Waiting for vendor response since 2026-01-20
Alpha | In Progress | 2026-01-06 | 2026-06-30 | 100000 | 45000 | Frontend dashboard build | In Progress | High | Diana Patel | Sprint 5 |  | Depends on API completion from Bob
Alpha | In Progress | 2026-01-06 | 2026-06-30 | 100000 | 45000 | Write integration tests | To Do | Medium | Eve Johnson | Sprint 5 |  | Waiting for authentication API and payment gateway to be complete
Alpha | In Progress | 2026-01-06 | 2026-06-30 | 100000 | 45000 | Database migration scripts | Done | High | Frank Liu | Sprint 4
Alpha | In Progress | 2026-01-06 | 2026-06-30 | 100000 | 45000 | Performance load testing | To Do | Medium | Alice Chen | Sprint 5 |  | Prerequisite: all APIs must be deployed to staging
Alpha | In Progress | 2026-01-06 | 2026-06-30 | 100000 | 45000 | Security audit | To Do | High | Bob Martinez | Sprint 6 |  | Depends on authentication API completion
Alpha | In Progress | 2026-01-06 | 2026-06-30 | 100000 | 45000 | User acceptance testing | To Do | High | Charlie Kim | Sprint 6
Alpha | In Progress | 2026-01-06 | 2026-06-30 | 100000 | 45000 | Documentation update | To Do | Low | Diana Patel | Sprint 6
Beta | Planning | 2026-02-01 | 2026-08-31 | 150000 | 10000 | Requirements gathering | Done | High | Grace Wilson | Sprint 2
Beta | Planning | 2026-02-01 | 2026-08-31 | 150000 | 10000 | Stakeholder interviews | Done | High | Henry Obi | Sprint 2
Beta | Planning | 2026-02-01 | 2026-08-31 | 150000 | 10000 | Design mockups | In Progress | High | Grace Wilson | Sprint 3 |  | Client feedback pending - slow response from sponsor
Beta | Planning | 2026-02-01 | 2026-08-31 | 150000 | 10000 | Technical feasibility study | In Progress | Medium | Henry Obi | Sprint 3 |  | Waiting for infrastructure team capacity assessment
Beta | Planning | 2026-02-01 | 2026-08-31 | 150000 | 10000 | Data model design | To Do | High | Grace Wilson | Sprint 4 |  | Depends on technical feasibility study
Beta | Planning | 2026-02-01 | 2026-08-31 | 150000 | 10000 | API specification | To Do | Medium | Henry Obi | Sprint 4
Beta | Planning | 2026-02-01 | 2026-08-31 | 150000 | 10000 | Vendor selection | To Do | High | Grace Wilson | Sprint 4 |  | Blocked by procurement process - budget approval pending
Beta | Planning | 2026-02-01 | 2026-08-31 | 150000 | 10000 | Environment setup | To Do | Medium | Henry Obi | Sprint 5
Gamma | At Risk | 2025-09-01 | 2026-04-30 | 200000 | 185000 | Core platform migration | In Progress | Critical | Ivan Torres | Sprint 8 | Sprint 4;Sprint 5;Sprint 6;Sprint 7 | Repeatedly delayed due to legacy system complexity. Original estimate was Sprint 5 completion
Gamma | At Risk | 2025-09-01 | 2026-04-30 | 200000 | 185000 | Data migration pipeline | In Progress | Critical | Julia Park | Sprint 8 | Sprint 6;Sprint 7 | Blocked by core platform migration. Cannot proceed until platform is stable
Gamma | At Risk | 2025-09-01 | 2026-04-30 | 200000 | 185000 | User training material | On Hold | Medium | Karen Wright | Sprint 8 |  | On hold until migration is complete
Gamma | At Risk | 2025-09-01 | 2026-04-30 | 200000 | 185000 | Legacy system decommission | To Do | High | Ivan Torres | Sprint 9 |  | Depends on successful data migration validation
Gamma | At Risk | 2025-09-01 | 2026-04-30 | 200000 | 185000 | Rollback plan documentation | Done | High | Julia Park | Sprint 7
Gamma | At Risk | 2025-09-01 | 2026-04-30 | 200000 | 185000 | Performance benchmarking | To Do | Medium | Karen Wright | Sprint 9 |  | Prerequisite: core platform migration complete
Gamma | At Risk | 2025-09-01 | 2026-04-30 | 200000 | 185000 | Compliance verification | To Do | Critical | Ivan Torres | Sprint 9 |  | Waiting for legal team review
Gamma | At Risk | 2025-09-01 | 2026-04-30 | 200000 | 185000 | Go-live checklist | To Do | High | Julia Park | Sprint 10
Delta | In Progress | 2026-01-15 | 2026-07-31 | 80000 | 22000 | Mobile app wireframes | Done | High | Leo Nakamura | Sprint 3
Delta | In Progress | 2026-01-15 | 2026-07-31 | 80000 | 22000 | iOS prototype build | In Progress | High | Mia Santos | Sprint 5
Delta | In Progress | 2026-01-15 | 2026-07-31 | 80000 | 22000 | Android prototype build | In Progress | High | Leo Nakamura | Sprint 5
Delta | In Progress | 2026-01-15 | 2026-07-31 | 80000 | 22000 | Backend API development | In Progress | High | Mia Santos | Sprint 5 | Sprint 4 | Some carry-over from Sprint 4 due to scope creep
Delta | In Progress | 2026-01-15 | 2026-07-31 | 80000 | 22000 | Push notification service | To Do | Medium | Leo Nakamura | Sprint 6 |  | Depends on backend API
Delta | In Progress | 2026-01-15 | 2026-07-31 | 80000 | 22000 | User analytics integration | To Do | Low | Mia Santos | Sprint 6
Delta | In Progress | 2026-01-15 | 2026-07-31 | 80000 | 22000 | Beta testing programme | To Do | High | Leo Nakamura | Sprint 7
Delta | In Progress | 2026-01-15 | 2026-07-31 | 80000 | 22000 | App store submission prep | To Do | Medium | Mia Santos | Sprint 8
Epsilon | In Progress | 2025-11-01 | 2026-03-31 | 60000 | 58000 | Regulatory compliance audit | In Progress | Critical | Nora Bell | Sprint 6 | Sprint 4;Sprint 5 | Repeatedly extended. Auditor flagged 12 additional items in Sprint 5
Epsilon | In Progress | 2025-11-01 | 2026-03-31 | 60000 | 58000 | Policy document updates | In Progress | High | Oscar Ruiz | Sprint 6 | Sprint 5 | Waiting for compliance audit findings to finalise
Epsilon | In Progress | 2025-11-01 | 2026-03-31 | 60000 | 58000 | Staff training rollout | On Hold | High | Nora Bell | Sprint 6 |  | On hold - blocked by policy document completion
Epsilon | In Progress | 2025-11-01 | 2026-03-31 | 60000 | 58000 | System controls implementation | In Progress | Critical | Oscar Ruiz | Sprint 6 |  | Depends on audit recommendations
Epsilon | In Progress | 2025-11-01 | 2026-03-31 | 60000 | 58000 | External audit scheduling | To Do | High | Nora Bell | Sprint 7 |  | Cannot schedule until internal audit complete
Epsilon | In Progress | 2025-11-01 | 2026-03-31 | 60000 | 58000 | Board compliance report | To Do | Critical | Oscar Ruiz | Sprint 7 |  | Waiting for all audit streams to complete
Zeta | In Progress | 2026-01-20 | 2026-09-30 | 120000 | 15000 | Market research phase | Done | High | Priya Sharma | Sprint 2
Zeta | In Progress | 2026-01-20 | 2026-09-30 | 120000 | 15000 | Competitive analysis | Done | Medium | Quinn Foster | Sprint 2
Zeta | In Progress | 2026-01-20 | 2026-09-30 | 120000 | 15000 | Product strategy document | In Progress | High | Priya Sharma | Sprint 3
Zeta | In Progress | 2026-01-20 | 2026-09-30 | 120000 | 15000 | MVP feature prioritisation | In Progress | High | Quinn Foster | Sprint 3
Zeta | In Progress | 2026-01-20 | 2026-09-30 | 120000 | 15000 | UX research interviews | To Do | Medium | Priya Sharma | Sprint 4
Zeta | In Progress | 2026-01-20 | 2026-09-30 | 120000 | 15000 | Technical architecture design | To Do | High | Quinn Foster | Sprint 4 |  | Depends on product strategy finalisation
Zeta | In Progress | 2026-01-20 | 2026-09-30 | 120000 | 15000 | Prototype build | To Do | High | Priya Sharma | Sprint 5
Zeta | In Progress | 2026-01-20 | 2026-09-30 | 120000 | 15000 | User testing round 1 | To Do | Medium | Quinn Foster | Sprint 6