Portfolio Risk & Value Briefing — Steering Committee

# Executive Summary

The portfolio comprises 6 active projects. 5 are rated Red, 1 Amber, and 0 Green. 22 risks have been identified, with 6 projects requiring attention. Projects requiring immediate attention: Alpha, Epsilon, Gamma, Beta, Zeta.

# Project Overview

| Project | Status | RAG | Risks | Top Risk |
| --- | --- | --- | --- | --- |
| Alpha | In Progress | Red | 5 | Task 'Implement payment gateway' is blocked |
| Epsilon | In Progress | Red | 5 | Task 'Staff training rollout' is on hold |
| Gamma | At Risk | Red | 5 | Task 'Data migration pipeline' has blocker in comments |
| Beta | Planning | Red | 5 | Task 'Vendor selection' has blocker in comments |
| Zeta | In Progress | Red | 1 | Task 'Technical architecture design' has 1 dependency |
| Delta | In Progress | Amber | 1 | Task 'Push notification service' has 1 dependency |

# Top Portfolio Risks

[Critical] 1. Task 'Implement payment gateway' is blocked

In project Alpha, the critical-priority task 'Implement payment gateway' (assigned to Charlie Kim) has status 'Blocked' and comments indicate a blocker: "Blocked by third-party vendor API changes. Waiting for vendor response...".

Mitigation: Escalate the blocker on 'Implement payment gateway' — identify the blocking party and set a resolution deadline. Review the dependency: Blocked by third-party vendor API changes. Waiting for vendor response.... Assign an owner to chase resolution. Consider this a priority escalation — critical-priority work is stalled.

[Critical] 2. Task 'Implement payment gateway' has 2 dependencies

In project Alpha, the critical-priority task 'Implement payment gateway' (assigned to Charlie Kim) has 2 dependency indicators in comments: "third-party vendor API changes" (blocked by); "vendor response since 2026-01-20" (waiting for).

Mitigation: Task 'Implement payment gateway' has 2 dependencies — review whether all are genuine blockers or if any can be decoupled. Assign an owner to each dependency for resolution tracking. As a critical-priority item, unresolved dependencies should be escalated to the project lead.

[Critical] 3. Task 'Staff training rollout' is on hold

In project Epsilon, the high-priority task 'Staff training rollout' (assigned to Nora Bell) has status 'On Hold' and comments indicate a blocker: "On hold - blocked by policy document completion".

Mitigation: Escalate the blocker on 'Staff training rollout' — identify the blocking party and set a resolution deadline. Review the dependency: On hold - blocked by policy document completion. Assign an owner to chase resolution. Consider this a priority escalation — high-priority work is stalled.

[Critical] 4. Task 'Board compliance report' has blocker in comments

In project Epsilon, the critical-priority task 'Board compliance report' (assigned to Oscar Ruiz) has a blocker indicated in comments: "Waiting for all audit streams to complete".

Mitigation: Review the dependency: Waiting for all audit streams to complete. Assign an owner to chase resolution. Consider this a priority escalation — critical-priority work is stalled.

[Critical] 5. Project 'Epsilon' has consumed 97% of budget with 27% of time remaining

Project Epsilon has spent 58,000 of its 60,000 budget (97% consumed). However, 27% of the project timeline remains (2026-03-31 end date). At the current burn rate, the project will exhaust its budget before completion.

Mitigation: Review spending trajectory on Epsilon. Identify the largest cost drivers and assess whether scope reduction, timeline extension, or additional funding is needed. Flag to steering committee for decision.

# Recommended Decisions

1. Escalate Alpha, Epsilon, Gamma to executive review — these projects have Critical/High risks requiring immediate intervention.

2. Review budget allocation for Gamma, Epsilon — current burn rate indicates budget exhaustion before delivery completion.

3. Unblock delivery on Alpha — assign owners to resolve blockers and set resolution deadlines within 5 working days.

# Key Talking Points

Portfolio health: 5 of 6 projects are Red status, requiring leadership attention this cycle.

The most common risk category is 'Dependency' (11 instances across the portfolio).

Key question for the committee: Are we comfortable with the current risk exposure, or do we need to reallocate resources?